## Project Schedule
Task No. | Task Description | Task Duration (in Weeks) | Start Date | End Date | Status | Progress
Phase 1: Research & Analysis |  | 6 | 2023-09-25 | 2023-11-13 | complete | done
1 | Review research papers and journals | 6 | 2023-09-25 | 2023-11-01 | complete | done
1.1 | Reviewing existing applications and technologies | 4 | 2023-10-09 | 2023-11-01 | complete | done
1.2 | Complete Project Definition Form | 2 | 2023-09-27 | 2023-10-10 | complete | done
1.3 | Apply for ethics approval | 1 | 2023-10-27 | 2023-11-17 | complete | done
1.4 | Conduct Knowledge Elicitation/Survey | 3 | 2023-11-17 | 2023-11-26 | complete | done
1.5 | Requirements Specification | 1 | 2023-11-06 | 2023-12-01 | complete | done
Phase 2: Planning and Designing |  | 4 | 2023-12-01 | 2023-12-15 | complete | done
2 | Researching tools and technologies | 2 | 2023-10-17 | 2023-12-05 | complete | done
2.1 | Backend design | 2 | 2023-12-05 | 2023-12-15 | complete | done
2.2 | UI design | Occurs at the same time as 2.1 | 2023-12-05 | 2023-12-15 | complete | done
Phase 3: Implement and Testing |  | 15 | 2023-12-11 | 2023-03-18 | complete | done
3 | Initialise project repository | 1 | 2023-12-02 | 2023-12-03 | complete | done
3.1 | Develop Application | 9 | 2023-12-03 | 2024-02-29 | complete | done
3.2 | Testing application | 2 | 2024-03-01 | 2024-03-15 | complete | done
3.3 | Perform Application Benchmark | 1 | 2024-03-01 | 2024-03-04 | complete | done
3.4 | Perform User Acceptance Testing | Same time as 3.2.1 | 2024-03-01 | 2024-03-06 | complete | done
3.5 | Analyse Test Results | 2 | 2024-03-01 | 2024-03-14 | complete | done
3.6 | Analyse benchmark results | Same time as 3.2.3 | 2024-03-01 | 2024-03-14 | complete | done
Phase 4: Evaluation and Review |  | 5 | 2024-03-18 | 2024-04-15 | complete | done
4 | Apply for ethics approval | 1 | 2024-03-18 | 2024-03-25 | complete | done
4.1 | Usability testing of application | 2 | 2024-03-25 | 2024-04-08 | complete | done
4.2 | Self-reflection of Project | 1 | 2024-04-08 | 2024-04-15 | complete | done
Report Writeup | [5 empty] | not yet started
1 | Complete Project Definition Form | 3 | 2023-09-27 | 2023-10-13 | complete | done
2 | Submit Term 1 report | 7 | 2023-10-20 | 2023-12-15 | complete | done
3 | Submit Final Report |  | 2024-01-01 | 2024-04-22 | incomplete | 109
3 | Report Writeup | TBC | Start of new year | Until deadlune (on blackboard) |  | not yet started
Formulas:
Progress = IF([Status] = "complete","done",IF([Status] = "incomplete", (IF([Start Date] < NOW(),DATEDIF([Start Date],NOW(),"d"), 0)), "not yet started"))

## Assessment Schedules
Task ID | Task Description | Task Duration (in Weeks) | Start Date | End Date | Status | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-29 | 2023-09-30 | 2023-10-01 | 2023-10-02 | 2023-10-03 | 2023-10-04 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-08 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 | 2023-10-13 | 2023-10-14 | 2023-10-15 | 2023-10-16 | 2023-10-17 | 2023-10-18 | 2023-10-19 | 2023-10-20 | 2023-10-21 | 2023-10-22 | 2023-10-23 | 2023-10-24 | 2023-10-25 | 2023-10-26 | 2023-10-27 | 2023-10-28 | 2023-10-29 | 2023-10-30 | 2023-10-31 | 2023-11-01 | 2023-11-02 | 2023-11-03 | 2023-11-04 | 2023-11-05 | 2023-11-06 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 | 2023-11-11 | 2023-11-12 | 2023-11-13 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 | 2023-11-18 | 2023-11-19 | 2023-11-20 | 2023-11-21 | 2023-11-22 | 2023-11-23 | 2023-11-24 | 2023-11-25 | 2023-11-26 | 2023-11-27 | 2023-11-28 | 2023-11-29 | 2023-11-30 | 2023-12-01 | 2023-12-02 | 2023-12-03 | 2023-12-04 | 2023-12-05 | 2023-12-06 | 2023-12-07 | 2023-12-08 | 2023-12-09 | 2023-12-10 | 2023-12-11 | 2023-12-12 | 2023-12-13 | 2023-12-14 | 2023-12-15 | 2023-12-16 | 2023-12-17 | 2023-12-18 | 2023-12-19 | 2023-12-20 | 2023-12-21 | 2023-12-22 | 2023-12-23 | 2023-12-24 | 2023-12-25 | 2023-12-26 | 2023-12-27 | 2023-12-28 | 2023-12-29 | 2023-12-30 | 2023-12-31 | 2024-01-01 | 2024-01-02 | 2024-01-03 | 2024-01-04 | 2024-01-05 | 2024-01-06 | 2024-01-07 | 2024-01-08 | 2024-01-09 | 2024-01-10 | 2024-01-11 | 2024-01-12 | 2024-01-13 | 2024-01-14 | 2024-01-15 | 2024-01-16 | 2024-01-17 | 2024-01-18 | 2024-01-19 | 2024-01-20 | 2024-01-21 | 2024-01-22 | 2024-01-23 | 2024-01-24 | 2024-01-25 | 2024-01-26 | 2024-01-27 | 2024-01-28 | 2024-01-29 | 2024-01-30 | 2024-01-31 | 2024-02-01 | 2024-02-02 | 2024-02-03 | 2024-02-04 | 2024-02-05 | 2024-02-06 | 2024-02-07 | 2024-02-08 | 2024-02-09 | 2024-02-10 | 2024-02-11 | 2024-02-12 | 2024-02-13 | 2024-02-14 | 2024-02-15 | 2024-02-16 | 2024-02-17 | 2024-02-18 | 2024-02-19 | 2024-02-20 | 2024-02-21 | 2024-02-22 | 2024-02-23 | 2024-02-24 | 2024-02-25 | 2024-02-26 | 2024-02-27 | 2024-02-28 | 2024-02-29 | 2024-03-01 | 2024-03-02 | 2024-03-03 | 2024-03-04 | 2024-03-05 | 2024-03-06 | 2024-03-07 | 2024-03-08 | 2024-03-09 | 2024-03-10 | 2024-03-11 | 2024-03-12 | 2024-03-13 | 2024-03-14 | 2024-03-15 | 2024-03-16 | 2024-03-17 | 2024-03-18 | 2024-03-19 | 2024-03-20 | 2024-03-21 | 2024-03-22 | 2024-03-23 | 2024-03-24 | 2024-03-25 | 2024-03-26 | 2024-03-27 | 2024-03-28 | 2024-03-29 | 2024-03-30 | 2024-03-31 | 2024-04-01 | 2024-04-02 | 2024-04-03 | 2024-04-04 | 2024-04-05 | 2024-04-06 | 2024-04-07 | 2024-04-08 | 2024-04-09 | 2024-04-10 | 2024-04-11 | 2024-04-12 | 2024-04-13 | 2024-04-14 | 2024-04-15 | 2024-04-16 | 2024-04-17 | 2024-04-18 | 2024-04-19 | 2024-04-20 | 2024-04-21 | 2024-04-22 | 2024-04-23 | 2024-04-24 | 2024-04-25 | 2024-04-26
Phase 1: Research & Analysis |  | 5 | 2023-09-25 | 2023-11-01
1.1 | Complete Project Definition Form | 2 | 2023-09-27 | 2023-10-10 | incomplete
1.2 | Create First Report
Phase 2: Planning and Designing |  | 4 | 2023-11-01 | 2023-12-02
2 | First draft version of final report.
Phase 3: Implement and Testing |  | 14 | 2023-11-30 | 2024-03-15
3 | Prepare final report
Phase 3: Evaluation and Review |  | 4 | 2024-03-07 | 2024-04-07
4 | Prepare for demo

## Keys
Keys
Concurrent
Task of Phase 1
Task of Phase 2
Task of Phase 3
Task of Phase 4
Sub-task
Contingency Time